## Instructions
Progressive Rehabilitation and Closure Plan Schedule template
Instructions
General Instructions:
- This form can be used for completing a PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).
- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.
- A default value of one (1) Rehabilitation Area (RA) is represented by one RA sheets below (RA1).
- A default value of one (1) Improvement Area (IA) is represented by one IA sheet below (IA1).
- To record additional RAs for your project make a copy of the RA sheet below and update it to the relevant RA number (i.e. RA2).
- To record additional IAs for your project make a copy of the IA sheet below and update it to the relevant IA number (i.e. IA2).
- To remove the IA sheet if there is no IA for your project, delete the IA sheet below.
- Each RA and IA sheet contains two separate excel tables (yellow and blue) for recording the time-based rehabilitation milestones.
- Add a new column or row to each table as required for your information requirements.
- Two (2) separate sheets below exist for recording the "Rehabilitation Area Milestones" and "Improvement Area Milestones".
- Delete the Improvement Area Milestone sheet if it does not apply to your project.
- Delete additional rows in either sheet if they do not apply to your project.
- See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.
Further Instructions when inputting PMLUs
Headings under Rehabilitation Area (RA) sheets
Rehabilitation area - The rehabilitation area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same PMLU and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.
Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence. The milestone reference for the first milestone must be included in the heading.
PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Rehabilitation Area Milestones sheet
Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
Further Instructions when inputting NUMAs
Headings under Improvement Area (IA) sheets
Improvement area - The improvement area must align with the spatial information included in the rehabilitation planning part of the PRC plan. This area must have the same NUMA and same milestones applied to the whole area.
Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.
Total size (ha) - Total size of improvement area in hectares.
Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence. The milestone reference for the first milestone must be included in the heading.
NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan and in the proposed final site design.
Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas becomes available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.
Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.
Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.
Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones sheet with the detailed milestone criteria. The milestones must be achieved consecutively.
Headings under Improvement Area Milestones sheet
Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.
ESR/2019/5103 • Version 1.00 • Effective: 01 November 2019 Department of Environment and Science

## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Ancillary infrastructure and services
Total rehabilitation area size (ha) |  |  |  | 19.76
Commencement of first milestone: RM1 |  |  |  | 2044-01-01
PMLU |  |  |  | Native ecosystem
Date area is available | 2044-01-01 | 2046-01-01 | 2047-01-01 | 2049-01-01 | 2055-01-01
Cumulative area available (ha) | 19.76 | 19.76 | 19.76 | 19.76 | 19.76
Milestone completed by | 2045-12-10 | 2046-12-10 | 2048-12-10 | 2054-12-10 | 2060-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 19.76
RM2 |  | 19.76
RM3 |  | 19.76
RM9 |  | 19.76
RM10 |  |  | 19.76
RM12 |  |  |  | 19.76
RM14 |  |  |  |  | 19.76
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Borrow pits and stockpiles
Total rehabilitation area size (ha) |  |  |  | 38.88
Commencement of first milestone: RM4 |  |  |  | 2044-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2050-01-01 | 2051-01-01 | 2056-01-01
Cumulative area available (ha) | 38.88 | 38.88 | 38.88
Milestone completed by | 2050-12-10 | 2055-12-10 | 2060-12-10
Milestone Reference | Cumulative area achieved (ha)
RM4 | 38.88
RM9 | 38.88
RM11 | 38.88
RM13 |  | 38.88
RM15 |  |  | 38.88
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Dams and diversion structures
Total rehabilitation area size (ha) |  |  |  | 32.28
Commencement of first milestone: RM1 |  |  |  | 2048-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2051-01-01 | 2052-01-01 | 2057-01-01 | 2058-01-01 | 2063-01-01
Cumulative area available (ha) | 32.28 | 32.28 | 32.28 | 32.28 | 32.28
Milestone completed by | 2051-12-10 | 2056-12-10 | 2057-12-10 | 2062-12-10 | 2067-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 32.28
RM2 | 32.28
RM5 |  | 32.28
RM9 |  | 32.28
RM11 |  |  | 32.28
RM13 |  |  |  | 32.28
RM15 |  |  |  |  | 32.28
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mineralised waste
Total rehabilitation area size (ha) |  |  |  | 22.4
Commencement of first milestone:RM2 |  |  |  | 2044-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2048-01-01 | 2051-01-01 | 2052-01-01 | 2053-01-01 | 2058-01-01
Cumulative area available (ha) | 22.4 | 22.4 | 22.4 | 22.4 | 22.4
Milestone completed by | 2050-12-10 | 2051-12-10 | 2052-12-10 | 2057-12-10 | 2062-12-10
Milestone Reference | Cumulative area achieved (ha)
RM2 | 22.4
RM6 |  | 22.4
RM9 |  | 22.4
RM11 |  |  | 22.4
RM13 |  |  |  | 22.4
RM15 |  |  |  |  | 22.4
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Mining and processing areas
Total rehabilitation area size (ha) |  |  |  | 180.53
Commencement of first milestone:RM2 |  |  |  | 2044-01-01
PMLU |  |  |  | Low intensity grazing
Date area is available | 2044-01-01 | 2045-01-01 | 2046-01-01 | 2046-01-01 | 2049-01-01 | 2050-01-01 | 2051-01-01 | 2055-01-01
Cumulative area available (ha) | 93.89 | 93.89 | 180.53 | 180.53 | 180.53 | 180.53 | 180.53 | 180.53
Milestone completed by | 2044-12-10 | 2045-12-10 | 2048-12-10 | 2050-12-10 | 2049-12-10 | 2054-12-10 | 2055-12-10 | 2059-12-10
Milestone Reference | 2044-01-01: Cumulative area achieved (ha)
RM1 | 2044-01-01: 93.89; 2046-01-01: 86.64
RM2 | 2044-01-01: 93.89; 2046-01-01: 86.64
RM6 | 2044-01-01: 93.89; 2046-01-01: 86.64
RM9 | 2045-01-01: 93.89; 2049-01-01: 86.64
RM11 | 2045-01-01: 93.89; 2049-01-01: 86.64
RM13 | 2046-01-01: 93.89; 2050-01-01: 86.64
RM15 | 2051-01-01: 93.89; 2055-01-01: 86.64
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Tailings Storage Facility (TSF)
Total rehabilitation area size (ha) |  |  |  | 107.83
Commencement of first milestone: RM1 |  |  |  | 2044-01-01
PMLU |  |  |  | Native ecosystem
Date area is available | 2044-01-01 | 2048-01-01 | 2051-01-01 | 2053-01-01 | 2058-01-01
Cumulative area available (ha) | 107.83 | 107.83 | 107.83 | 107.83 | 107.83
Milestone completed by | 2047-12-10 | 2050-12-10 | 2052-12-10 | 2057-12-10 | 2070-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 107.83
RM7 |  | 107.83
RM9 |  |  | 107.83
RM10 |  |  | 107.83
RM12 |  |  |  | 107.83
RM14 |  |  |  |  | 107.83
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Renewable energy infrastructure
Total rehabilitation area size (ha) |  |  |  | 67.1
Commencement of first milestone: RM1 |  |  |  | 2044-01-01
PMLU |  |  |  | Native ecosystem
Date area is available | 2044-01-01 | 2045-01-01 | 2046-01-01 | 2047-01-01 | 2050-01-01
Cumulative area available (ha) | 67.1 | 67.1 | 67.1 | 67.1 | 67.1
Milestone completed by | 2044-12-10 | 2045-12-10 | 2046-12-10 | 2049-12-10 | 2054-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 67.1
RM2 |  | 67.1
RM8 |  | 67.1
RM9 |  |  | 67.1
RM10 |  |  | 67.1
RM12 |  |  |  | 67.1
RM14 |  |  |  |  | 67.1
1) Insert new columns to the yellow table to include further rehabilitation milestone dates.
2) Insert new columns to the blue table to match rehabilitation milestone dates.
3) Insert new rows to the blue table to include additional rehabilitation milestone references.
4) Insert the relevant number in the "Milestone reference" column (i.e. RM1).

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure decommissioning and removal | For all areas: a) All buildings and associated infrastructure are dismantled and removed offsite. b) All hardstand and concrete areas are decommissioned and removed. c) Fences are removed. d) All pipelines are removed. e) Powerlines and supporting electrical infrastructure (above and below ground) are removed. f) Roads removed (with the exception of those being retained for future site access). g) Waste is removed. h) Drillholes, sediment ponds and sumps decommissioned. i) Machinery/ equipment not required for rehabilitation removed from site. For RA7: j) All infrastructure is decommissioned and removed from site in accordance with EODMP under the supervision of an AQP
RM2 | Removal of contaminated land | a) Contaminated land assessment is completed by a suitably qualified person. b) Any identified contaminated material is removed from the mine domain and disposed of at a licenced facility. c) Validation sampling determines that contaminant removal has been successful. d) The validation sampling report is accepted by a suitably qualified Contaminated Land Auditor stating that contamination removal has been successful.
RM3 | Landform development and reshaping - RA1 | a) Landform is shaped to be gently sloping, characteristic of the natural landform with natural drainage lines reinstated. b) Landform is ripped parallel to contour. c) Features such as large woody debris or boulders are situated to provide suitable habitat for the Purple Neck Rock Wallaby. d) RA1 is determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM4 | Landform development and reshaping - RA2 | a) Landform is shaped to be gently sloping, characteristic of the natural landform with natural drainage lines reinstated. b) Landform is ripped parallel to contour. c) RA2 determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM5 | Landform development and reshaping - RA3 | a) General earthworks completed. b) HPDE Liner removed. c) Dams filled with NAF or other suitable material. Material placed in 500mm lifts, watered and compacted. d) Landform is shaped to be gently sloping, characteristic of the natural landform with natural drainage lines reinstated. e) RA3 determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM6 | Landform development and reshaping - RA4/RA5 | a) Removal of waste rock. PAF material is disposed of underground. NAF material utilised in rehabilitation. b) Major earthworks are completed. c) Landform is shaped to be gently sloping, characteristic of the natural landform with natural drainage lines reinstated. d) Land reshaped to final landform design with suitable material as assessed by AQP and as per EODMP, where required. e) RA4/RA5 is determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM7 | Landform development and reshaping - RA6 | a) The construction of the cover system / cap has been certified by an appropriately qualified person as being consistent with the cover design. b) QAQC testing is completed post construction at a rate of at least 1 sample per ha and confirms depth of layers and permeability is to specified designs and no PAF material is present within the cover system. c) Primary monitoring locations have been established in representative locations recommended as an outcome of the trial mentioned in Condition PRCP5(e) and include: I. An automated meteorological station that records the following: rainfall (tipping bucket), i. evaporation, ii. relative humidity, iii. wind strength, iv. wind direction, and v. air temperature. II. piezometers within the tailings and capillary break layer, III. automated in situ water content and suction sensors in each layer of the cover system and in the tailings below the cover system that records data at 30 minute intervals (except in the capillary break), IV. temperature sensor in each layer of the cover system and in the tailings below the cover system that records data at 30 minute intervals, V. a lysimeter. d) Secondary monitoring locations have been established in representative locations recommended as an outcome of the trial mentioned in Condition PRCP5(e) and include in each layer of the cover system and in the tailings below the cover system: I. piezometers within the tailings and capillary break layer, II. automated in situ water content sensors in each layer of the cover system and in the tailings below the cover system that records data at 30 minute intervals (except in the capillary break). e) Temperature sensor in each layer of the cover system and in the tailings below the cover system that records data at 30 minute intervals. All sensors are calibrated to each material type using the manufacturers specifications. f) Lysimeters and associated drainage collection and monitoring system are installed in at least 3 locations that are recommended as an outcome of the trial mentioned in Condition PRCP5(e). g) Sediment capture flumes have been installed and calibrated at the base of the TSF embankment. h) All monitoring equipment has been installed and calibrated by an appropriately qualified person. i) Slopes of TSF surface have a grade of <1.5% j) Certification by an AQP that landform has been constructed according to the design and has achieved an acceptable factor of safety. k) Spillway is reinstated at RL 242.1m. Spillway has an approximate length of 330m and a longtitudinal grade of 2.0%. l) TSF is assessed as geotechnically stable by a suitably qualified geotechnical engineer. m) Features such as large woody debris or boulders are present to provide suitable habitat for the Purple Neck Rock Wallaby. n) TSF surface has been shaped to prevent ponding and concentration of surface water flow. o) Spillway is designed and constructed to support peak flood flow velocity. p) Average erosion rate of <5 t/ha/y with the maximum erosion rate at any point on the landform of <10 t/ha/y. q) Erosion rilling is <0.2m. r) No surface ponding. s) Installation of erosion and sediment control structures that comply with International Erosion Control Association (IECA).
RM8 | Landform development and reshaping - RA7 | a) Land reshaped to final landform design with suitable material as assessed by AQP and as per EODMP. b) Features such as large woody debris or boulders are situated to provide suitable habitat for the Purple Neck Rock Wallaby. c) RA7 is determined to be geotechnically stable by a suitably qualified geotechnical engineer.
RM9 | Surface preparation | a) Deep ripping of compacted surfaces, at least 300mm into soil profile, where required and avoiding habitat features associated with RM3 and RM8. b) An assessment of the need for soil amelioration undertaken and soil ameliorants such as fertiliser, gypsum and/or organic matter have been applied at rates determined by an appropriately qualified person. c) Topsoil placement of 0.1 - 0.2 m
RM10 | Revegetation (native ecosystem) | a) Seeding rate of 4 – 10 kg/ha is applied. b) Direct seeding species mix is endemic to Regional Ecosystem 1.11.2 and 1.7.7 on RA1 including Eucalyptus leucophloia, Corymbia terminalis, Corymbia capricornia with a groundcover of Aristida latifolia, Eriachne obtusa,Sporobolus australasicus,Themeda triandra, Triodia pungens. c) Direct seeding species mix is endemic to Regional Ecosystem 1.11.2 and 1.7.7 on RA6 including Aristida latifolia, Eriachne obtusa,Sporobolus australasicus,Themeda triandra, Triodia pungens. d) Direct seeding species mix is endemic to Regional Ecosystem 1.11.2a/1.7.7a and RE1.11.3a/1.3.13a on RA7, including the terrestrial species of Eucalyptus leucophloia, Corymbia terminalis and Corymbia capricornia with a groundcover of Aristida latifolia, Eriachne obtusa,Sporobolus australasicus, Themeda triandra and Triodia pungens. e) Direct seeding species mix on RA7 including riparian species of Eucalyptus camaldulensis, Corymbia capricornia, Sporobolus australasicus, Melaleuca species, Lophostemon species and other suitable wetland groundcover species in riparian vegetation zones. f) Deep rooting vegetation such as Eucalyptus Spp not present on RA6. g) Groundcover >50%.
RM11 | Revegetation (grazing) | a) Direct seeding is applied at a rate of 4 – 10 kg/ha. b) Direct seeding of native species including Eucalyptus leucophloia, Corymbia capricornia, Terminalia aridicola, Corymbia terminalis, Triodia pungens, Eucalyptus pruinose, Eremophila longifolia, Atalaya hemiglauca, Acacia chisholmi,i Atalaya hemiglauca, Carissa lanceolata as well as appropriate 3P grass species to support the PMLU. c) Pasture vegetation seeding creates cover >30%.
RM12 | Achievement of surface requirements (native ecosystem) | For all areas: a) Weed species in densities less than 10% total coverage. b) Average erosion rate of <5 t/ha/y with the maximum erosion rate at any point on the landform of <10 t/ha/y. c) Vegetation cover 70%. d) Species used in revegetation in RM10 remain present and showing evidence of natural recruitment. e) Surface water quality measured at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken on an event basis1 complies with ANZECC/ARMCANZ (2000) Table 3.4.1 for 95% protection level and Table 3.3.4 values for aquatic ecosystems (slightly to moderately disturbed). f) Stream sediment quality at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken twice a year (at end of wet season and end of dry season) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low. g) Quarterly groundwater monitoring at MB5, MB6, MB9S and MB9D demonstrate groundwater quality complies with groundwater trigger limits nominated in Schedule C – Table 8 of the EA. h) Soil testing indicates the following parameters are met: I. Rootzone EC <0.15mS/cm, II. Soil pH <9 and >6 as measured at any part of the root zone, III. Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). For RA6: i) There is no evidence of water ponding on the surface of the TSF. j) Continuous recording demonstrates seepage volume is decreasing. k) Seepage is collected and disposed of at an appropriately licensed facility. l) In-situ permeability and surface infiltration are not significant deacreasing compared with initial rates based on statisical analysis. For RA7: m) Certification from AQP that all actions required in EODMP to achieve surface requirements have been completed. n) All temporary erosion and sediment control and stormwater management structures have been removed. o) No erosion classified as “moderate” or “severe”3. p) Riparian monitoring is undertaken every year5, which shows a progressive improvement in the following attributes; tree species richness, bank stability, recruitment and projected foliage cover, or is similar to, representative reference ephemeral waterways in the region q) Rehabilitated watercourses are stable and do not create any upstream or downstream impacts, as certified by an AQP.
RM13 | Achievement of surface requirements (grazing) | a) Weed species in densities less than 10% total coverage. b) Pasture covers has reached 70% of surface area. c) Average erosion rate of <5 t/ha/y with the maximum erosion rate at any point on the landform of <10 t/ha/y. d) Surface water quality measured at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken on an event basis1 complies with ANZECC/ARMCANZ (2000) Table 3.4.1 for 95% protection level and Table 3.3.4 values for aquatic ecosystems (slightly disturbed). e) Stream sediment quality at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken twice a year (at end of wet season and end of dry season) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low. f) Quarterly groundwater monitoring at MB5, MB6, MB9S and MB9D demonstrate groundwater quality complies with groundwater trigger limits nominated in Schedule C – Table 8 of the EA. g) Soil testing indicates the following parameters are met: I. Rootzone EC <0.15mS/cm, II. Soil pH <9 and >6 as measured at any part of the root zone, III. Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). For RA5: h) Certification from AQP that all actions required in EODMP to achieve surface requirements have been completed.
RM14 | Achievement of post-mining land use to a stable condition (native ecosystem) | For all areas: a) Vegetation cover exceeds 70% of the surface area. b) All species used in RM10 show natural recruitment. c) Weed species in densities less than 10% total coverage. d) Native fauna observed or indicators of these species have been recorded. e) There is no evidence of seepage occurring within the mining tenure. f) Certification from an REPQ that the domain has achieved stable condition.4 g) Certification from an AQP that the landform achieved a factor of safety 1.5. h) All results from surface water quality measured at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken on an event basis1 complies with ANZECC/ARMCANZ (2000) Table 3.4.1 for 95% protection level and Table 3.3.4 values for aquatic ecosystems (slightly disturbed) for a minimum of 5 consecutive years.1 i) All results from stream sediment quality at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken twice a year (at end of wet season and end of dry season) complies with ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low for a minimum of 5 consecutive years. j) All results from quarterly groundwater monitoring at MB5, MB6, MB9S and MB9D demonstrate groundwater quality complies with groundwater trigger limits nominated in Schedule C – Table 8 of the EA for a minimum of 5 consecutive years. k) Soil testing undertaken at yearly intervals indicates the following parameters are met: I. Rootzone EC <0.15mS/cm, II. Soil pH <9 and >6 as measured at any part of the root zone, III. Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth). For RA1: l) No evidence of erosion classified as ‘Severe’3. m) No active erosion present as demonstrated by no increase in erosion ratings3 over time. For RA6: n) There is no evidence of water ponding on the surface of the TSF. o) Average erosion rate of <5 t/ha/y. p) No evidence of erosion classified as ‘moderate’ or 'severe'. q) No evidence of salt rise through the cover system of the TSF. r) In-situ permeability and surface infiltration are not significantly decreasing compared with initial rates based on statistical analysis. s) Results of monitoring gathered from primary and secondary monitoring stations established in RM7 demonstrate the following has been maintained for a minimum of 10 years: I. Hydraulic conductivity of the cover system is less than 1 x 10-8 m/s for at least 10 years, II. Net percolation through the cover into the tailings has been reduced to <5% of rainfall for at least 10 years as measured by primary and secondary monitoring locations and lysimeters, III. Water content of the reduced permeability layer is maintained above 85% over a 10 year period, IV. Temperature within the tailings has not increased over a 10 year period, V. Volumetric water content of tailings does not respond to rainfall events. For RA7: t) Certification by AQP that all actions as required in the EODMP to achieve a stable condition have been completed. u) No evidence of erosion classified as “moderate” or “severe”3. Riparian monitoring undertaken every year5 shows an achievement in the following attributes; tree species richness, bank stability, recruitment and projected foliage cover, which is similar to, representative reference ephemeral waterways in the region.
RM15 | Achievement of post-mining land use to a stable condition (grazing) | a) Weed species in densities less than 10% total coverage. b) Vegetation cover has reached 70%. c) All established species show natural recruitment. d) Land suitability assessment by an appropriately qualified person certifies land has achieved a post-mine land suitability2 of 42 or better. e) Minimum of 4 palatable perennial pasture species and 2 shade tree species established. f) No evidence of erosion classified as ‘Severe’3. g) No active erosion present as demonstrated by no increase in erosion ratings3 over time. h) There is no evidence of seepage occurring within the mining tenure. i) Certification from an REPQ that the domain has achieved stable condition.4 j) Certification from an AQP that the landform achieved a factor of safety 1.5. k) All results from surface water quality measured at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) complies with ANZECC/ARMCANZ (2000) Table 3.4.1 for 95% protection level and Table 3.3.4 values for aquatic ecosystems (slightly to moderately disturbed) for a minimum of 5 consecutive years.1 l) All results from stream sediment at downstream monitoring sites (CT3-08 (MS2), CC-05, CC-15, MS8 (SN-15), SC-29 (MS5), SN-05 (MS8 REF), SN-08 (MS5 Ref) and DR-18) undertaken twice a year (at end of wet season and end of dry season) complies with limits set for low risk and no adverse effects in ANZECC/ARMCANZ (2000) Interim Sediment Quality Guidelines – low for a minimum of 5 consecutive years. m) All results from quarterly groundwater monitoring at MB5, MB6, MB9S and MB9D demonstrate groundwater quality complies with groundwater trigger limits nominated in Schedule C – Table 8 of the EA for a minimum of 5 consecutive years. n) Soil testing undertaken at yearly intervals indicates the following parameters are met: PAWC >50 at Red Plain and Pocket soil types, I. Rootzone EC <0.15mS/cm, II. Soil pH <9 and >6 as measured at any part of the root zone, III. Exchangeable Sodium Percentage (ESP%) <5% (at 0-10cm depth), IV. Carrying capacity is suitable to support a sustainable level of grazing. For RA5: o) Certification by AQP that all actions as required in the EODMP to achieve a stable condition have been completed.
1) Insert new rows below the table to record more Rehabilitation Area Milestones for the project
2) Ensure all Rehabilitation Milestones recorded in this table align with those included in the RA sheets in this form.
3) See the PRCP guideline before developing site-specific Rehabilitation Area Milestones

## Improvement Area Milestones
Milestone reference | Management milestone | Milestone criteria
MM1
MM2
MM3
MM4
MM5
MM6
MM7
MM8
MM9
MM10
1) Insert new rows below the table to record more Improvement Area Milestones for the project
2) Ensure all Management Milestones recorded in this table align with those included in the IA sheets in this form.
3) See the PRCP guideline before developing site-specific Improvement Area Milestones