## RA1
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA1
Relevant activities |  |  |  | Open Cut Pits (Pit 1, Pit 2, Pit 3, Pit 4, Pit 6)
Total rehabilitation area size (ha) |  |  |  | 13.33
Commencement of first milestone: RM1 |  |  |  | 2026-11-01
PMLU |  |  |  | Native Ecosystem
Date area is available | 2026-11-01 | 2028-12-10 | 2029-12-10 | 2031-12-10 | 2028-12-10 | 2030-12-10 | 2032-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10
Cumulative area available (ha) | 1.06 | 6.95 | 13.33 | 13.33 | 13.33 | 13.33 | 13.33 | 13.33 | 13.33 | 13.33
Milestone completed by | 2028-12-10 | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2035-12-10 | 2037-12-10 | 2039-12-10 | 2043-12-10 | 1945-12-10 | 2047-12-10
Milestone Reference | Cumulative area achieved (ha)
RM1 | 1.06 | 6.95 | 13.33
RM3 | 1.06 | 6.95 | 13.33
RM5 | 1.06 | 6.95 | 13.33
RM6 | 1.06 |  | 6.95 | 13.33
RM7 |  |  |  |  | 1.06 | 6.95 | 13.33
RM8 | [7 empty] | 1.06 | 6.95 | 13.33

## RA2
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA2
Relevant activities |  |  |  | Former waste rock dumps (WRDs)
Total rehabilitation area size (ha) |  |  |  | 16.79
Commencement of first milestone: RM1 |  |  |  | 2028-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2028-12-10 | 2030-12-10 | 2032-12-10 | 2032-12-10 | 2033-12-10 | 2039-12-10 | 2040-12-10 | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 6.42 | 16.79 | 16.79 | 16.79 | 16.79 | 16.79 | 16.79
Milestone completed by | 2030-12-10 | 2032-12-10 | 2033-12-10 | 2039-12-10 | 2040-12-10 | 2047-12-10 | 2048-12-10 | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 6.42 | 16.79
RM3 | 6.42 | 16.79
RM5 | 6.42 | 16.79
RM6 |  | 6.42 | 16.79
RM7 |  |  |  | 6.42 | 16.79
RM8 | [5 empty] | 6.42 | 16.79

## RA3
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA3
Relevant activities |  |  |  | Low Grade Waste Rock Dump
Total rehabilitation area size (ha) |  |  |  | 5.11
Commencement of first milestone: RM1 |  |  |  | 2030-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2042-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11 | 5.11
Milestone completed by | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2042-12-10 | 2050-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 5.11
RM3 |  | 5.11
RM4 |  |  | 5.11
RM5 |  |  |  | 5.11
RM6 |  |  |  |  | 5.11
RM7 | [5 empty] | 5.11
RM8 | [6 empty] | 5.11

## RA4
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA4
Relevant activities |  |  |  | Mine Infrastructure (ROM Pad, Administration, Camp, Maintenance, Storage and Irrigation area, Explosives Magazine, Laydown, Mine Work Areas)
Total rehabilitation area size (ha) |  |  |  | 3.64
Commencement of first milestone: RM1 |  |  |  | 2030-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2030-12-10 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2042-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64 | 3.64
Milestone completed by | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2035-12-10 | 2042-12-10 | 2050-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 3.64
RM2 |  | 3.64
RM3 |  |  | 3.64
RM5 |  |  |  | 3.64
RM6 |  |  |  |  | 3.64
RM7 | [5 empty] | 3.64
RM8 | [6 empty] | 3.64

## RA5
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA5
Relevant activities |  |  |  | Water Infrastructure (Water Storage Dam, Sediment Dams, Water Diversions, Tank Farm)
Total rehabilitation area size (ha) |  |  |  | 12.95
Commencement of first milestone: RM1 |  |  |  | 2031-04-01
PMLU |  |  |  | Native Ecosystem
Date area is available | 2031-04-01 | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2041-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 12.95 | 12.95 | 12.95 | 12.95 | 12.95 | 12.95
Milestone completed by | 2031-12-10 | 2032-12-10 | 2033-12-10 | 2034-12-10 | 2041-12-10 | 2049-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 12.95
RM3 |  | 12.95
RM5 |  |  | 12.95
RM6 |  |  |  | 12.95
RM7 |  |  |  |  | 12.95
RM8 | [5 empty] | 12.95

## RA6
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA6
Relevant activities |  |  |  | Haul roads and existing access tracks
Total rehabilitation area size (ha) |  |  |  | 9.59
Commencement of first milestone: RM1 |  |  |  | 2034-12-10
PMLU |  |  |  | Native Ecosystem
Date area is available | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2045-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 9.59 | 9.59 | 9.59 | 9.59 | 9.59 | 9.59
Milestone completed by | 2035-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2045-12-10 | 2053-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 9.59
RM3 |  | 9.59
RM5 |  |  | 9.59
RM6 |  |  |  | 9.59
RM7 |  |  |  |  | 9.59
RM8 | [5 empty] | 9.59

## RA7
Post-mining land uses (PMLU)
Rehabilitation area |  |  |  | RA7
Relevant activities |  |  |  | Topsoil Stockpiles
Total rehabilitation area size (ha) |  |  |  | 1.37
Commencement of first milestone: RM1 |  |  |  | 2033-05-01
PMLU |  |  |  | Native Ecosystem
Date area is available | 2034-12-10 | 2035-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2045-12-10 | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx | 10/12/xxxx
Cumulative area available (ha) | 1.37 | 1.37 | 1.37 | 1.37 | 1.37 | 1.37
Milestone completed by | 2035-12-10 | 2036-12-10 | 2037-12-10 | 2038-12-10 | 2045-12-10 | 2053-12-10 | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx | xx/xx/xxxx
Milestone Reference | Cumulative area achieved (ha)
RM1 | 1.37
RM3 |  | 1.37
RM5 |  |  | 1.37
RM6 |  |  |  | 1.37
RM7 |  |  |  |  | 1.37
RM8 | [5 empty] | 1.37

## Rehabilitation Area Milestones
Milestone reference | Rehabilitation milestone | Milestone criteria
RM1 | Infrastructure Decommissioning and Removal | 1.1 With the exception of any infrastructure to remain as part of the post-mining land use (PMLU), the following are complete: (a) All services disconnected, terminated and removed; (b) All pipelines drained and decommissioned; (c) All buildings and associated infrastructure are demolished and removed; (d) All hardstand, concrete areas and roads (concrete, bitumen, gravel, blue metal, aggregate, etc.) removed; (e) All fencing and associated foundations removed; (f) All machinery and equipment not required for rehabilitation works removed from site; (g) All surface water drainage infrastructure removed; (h) All waste not authorised to be disposed of on-site under environmental authority P-EA-100326888 removed; (i) All drillholes, bores, sediment ponds and sumps decommissioned; and (j) All dams are dewatered and desilted. 1.2 An independent appropriately qualified person (AQP) has certified the achievement of RM1.1.
RM2 | Identification, remediation and removal of contaminated land | 2.1 Contaminated land investigations (investigation, remediation and validation) completed by a suitably qualified person (SQP) in accordance with appropriate guidance, including but not limited to the National Environment Protection (Assessment of Site Contamination) Measure (ASC NEPM) and National Remediation Framework (NRF). 2.2 Contaminated water and sediment removed from dams. 2.3 Contaminated and hazardous material either remediated in-situ or removed/transported to facility lawfully able to accept the material. 2.4 Validation sampling determines that contaminant removal has been successful to the extent that no contamination unsuitable for the PMLU remains or is occurring 2.5 Contaminated Land Auditor certifies that no contamination unsuitable for the PMLU remains or is occurring.
RM3 | Landform Development and Reshaping / Reprofiling | 3.1 All major earthworks (including reshaping, pushing/trimming) are completed in accordance with the design specification provided by an AQP. 3.2 Relevant structures developed and/or reshaped, such that they are consistent with the landform closure design report. 3.3 An “As Constructed Report” prepared which details and justifies all variations to the design, including a certification that such variations will not affect the design performance. 3.4 Constructed landform achieves geotechnical stability with a Factor of Safety (FoS) ≥ 1.5, which includes consideration of flood stress. 3.5 Disturbed slopes align with those stated within the landform closure design report. 3.6 Erosion and sediment control (ESC) and drainage structures are installed and functioning as per design specifications and certified by an AQP. 3.7 An independent AQP has surveyed the final landform and certified that RM3.1-3.6 have been achieved.
RM4 | Installation of a cover system | 4.1 Landform design has been reviewed and a detailed cover system design completed. 4.2 The cover system has been installed as per design. 4.3 All potentially acid forming (PAF) material is located within an AQP designed and engineered cell, fully encapsulated in compacted non-acid forming (NAF) material. 4.4 The cover system surface is water shedding and does not display surface ponding. 4.5 The cover system displays erosional stability, is geotechnically stable and supports the PMLU. 4.6 An independent AQP has certified that RM4.1-4.5 have been achieved.
RM5 | Surface preparation | 5.1 Assessment of growth media characteristics and the development of an amelioration and physical treatment plan is completed by an AQP. 5.2 Ameliorant and physical treatments such as fertilisers, lime, gypsum and/or organic matter, are applied as identified in criteria RM5.1. 5.3 Topsoil/growth media placement of a minimum 200mm. 5.4 Deep ripping of compacted surfaces at least 300mm, (or refusal) into soil/subsoil profile along contour of slopes. 5.5 Following amelioration as per criteria RM5.1 and RM5.2, representative soil testing of growth media confirms: (a) pH in the range of 6-8.5; (b) Electrical Conductivity (saturated extract) (dS/m) ≤2 (2,000 µS/cm); (c) Exchangeable sodium percentage (ESP) (%) < 6; and (d) Emerson aggregate class: ≥ 4. 5.6 Growth media and suitability is assessed and documented by an AQP as suitable for the PMLU and target vegetation establishment. 5.7 The surface and groundwater monitoring network are installed, and monitoring is underway (one year of sampling undertaken). 5.8 Independent AQP has certified the plan in RM5.1 and achievement of RM5.2-5.7.
RM6 | Revegetation | 6.1 Seeding has been completed using recommended seeding mix in Appendix 1 - Revegetation Species List at a rate of 1-2kg/ha for tree species and 7-9kg/ha for grass/shrub/forb species, or as otherwise specified by the AQP. 6.2 Species chosen reflect Regional Ecosystems (REs) 2.10.5a, 9.5.10a or 9.12.11. 6.3 Non-native seeds must not be used for the revegetation (except when sterile cover crops are used). 6.4 Timing of seeding aligned with wet weather to coincide with elevated levels of soil moisture. 6.5 Stock exclusion fencing installed around all areas that have been seeded. 6.6 Independent AQP certifies achievement of RM6.1-6.5.
RM7 | Achievement of surface requirements | 7.1 Species used in revegetation remain present and show evidence of natural recruitment. Evidence of flora recruitment from rehabilitation monitoring data. 7.2 Weed presence is less than 5% of total vegetative cover; 7.3 Absence of ecosystem altering weeds. 7.4 Total vegetative groundcover ≥ 60%. 7.5 Total groundcover (combination of vegetative cover, other organic material (i.e., sticks, leaf litter) and inorganic material (i.e., rocks) ≥ 70%. 7.6 No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Appendix 2 – Erosion classification framework. 7.7 Any erosion present will not compromise the achievement of a PMLU to a stable condition. 7.8 Erosion requiring intervention has been remediated and does not impact achieving the PMLU. 7.9 Corrective actions arising from the routine inspections program have been undertaken and recorded. 7.10 Surface water runoff has been collected across representative areas of rehabilitation when surface flows occur, and it is safe to do so. 7.11 Surface water runoff complies with Appendix 3 – Surface water quality limits. 7.12 The growth media (topsoil and subsoil) physical, chemical and biological properties do not limit vegetation cover performance or restrict the potential effective depth of rooting. 7.13 A BioCondition assessment is completed by an AQP using the methodology outlined in the latest version of the Queensland Herbarium’s ‘BioCondition Assessment Manual’. 7.14 The BioCondition assessment completed under RM7.13 complies with the PRCP Benchmark for the PMLU, as per Appendix 4 – PRCP Benchmarks for Rehabilitation Areas. 7.15 Independent AQP certifies achievement of RM7.1-7.14.
RM8 | Achievement of post-mining land use to a stable condition | 8.1 Safety hazards in the rehabilitation area are not significantly different to surrounding unmined landscapes subject to the same land use. 8.2 The land is structurally and erosionally stable. 8.3 The final landform is geotechnically stable and achieved a FOS ≥ 1.5. 8.4 A BioCondition Assessment is completed by an AQP using the methodology outlined in the latest version of the Queensland Herbarium’s ‘BioCondition Assessment Manual’ 8.5 The BioCondition assessment completed under RM8.4 complies with the PRCP Benchmark for the PMLU, as per Appendix 4 – PRCP Benchmarks for Rehabilitation Areas. 8.6 Total vegetative ground ≥ 60 %. 8.7 Weed presence is a maximum of 5% of total vegetative cover as confirmed by an AQP in annual monitoring. 8.8 Restricted invasive plants (as defined in the Biosecurity Act 2014) comprise ≤ 5% of vegetation groundcover. 8.9 Absence of ecosystem altering weeds. 8.10 No evidence of erosion classified as ‘moderate’ or ‘severe’ as defined by Appendix 2 - Erosion classification framework. 8.11 Any erosion present will not compromise the achievement of a PMLU to a stable condition. 8.12 No evidence of scouring, overtopping, sedimentation or destabilisation in or associated with erosion and sediment control and engineered drainage structures. 8.13 Total ground cover (combination of vegetative cover, other organic material (i.e. sticks, leaf litter) and inorganic material (i.e. rocks)) ≥ 70% for erosional stability. 8.14 Sediment and erosion control structures removed as certified by AQP and rehabilitated consistent with the PMLU. 8.15 Stock exclusion fencing removed from around revegetation areas. 8.16 Surface water runoff complies with Appendix 3 – Surface water quality limits. 8.17 Surface water quality results monitored monthly during flow, but not limited to, downstream at the locations listed in Appendix 5 – Surface water monitoring locations, must not exceed the limits in Appendix 3 – Surface water quality limits, for a minimum of 3 consecutive years. 8.18 If the surface water quality exceeds the criteria RM8.17, the applicable upstream site must be compared to the downstream site result; and the quality result measured at a downstream site must be equal to or less than the quality result measured at the applicable upstream site1. 8.19 For a minimum of 3 consecutive years groundwater quality, must be monitored quarterly, but not limited to, locations specified in Appendix 6 – Groundwater monitoring locations, for all quality characteristics listed in Appendix 7 – Groundwater quality limits. 8.20 Groundwater quality results must not exceed the limits specified in Appendix 7 – Groundwater quality limits, for 3 consecutive results. 8.21 Groundwater level is monitored quarterly and for a minimum of 3 consecutive years. 8.22 Soil testing of growth media confirms the topsoil and subsoil physical, chemical and biological properties are not limiting vegetation cover performance (e.g. nutrient availability, drought stress). 8.23 Final landform survey confirms no built structures remain 8.24 There is no evidence indicating an adverse change to the contaminated land status has occurred post the completion of RM2. 8.25 Independent AQP certifies achievement of RM8.1-8.24.
1For pH and electrical conductivity, the quality result measured at the downstream location must be within the prescribed range. However, where pH or electrical conductivity at the downstream location is greater-than (>) the highest limit in the range, the pH or electrical conductivity at the applicable upstream location must be greater-than or equal-to (≥) the downstream location. Conversely, where pH at the downstream location is less than (<) the lowest limit in the range, the upstream pH at the applicable upstream location must be less-than or equal-to (≤) the downstream location.
Appendix 1 - Revegetation Species List
Appendix 2 - Erosion Classification Framework
Appendix 3 - Surface Water Quality Limits
Appendix 4 – PRCP Benchmarks for Rehabilitation Areas
Appendix 5 – Surface water monitoring locations
Appendix 6 – Groundwater monitoring locations
Appendix 7 – Groundwater quality limits