# General Instructions

- This form or ERS/2019/5103 must be used for completing a proposed PRCP schedule for the submission of a progressive rehabilitation and closure plan (PRC plan).

- See the PRCP schedule section of the PRC plan guideline (ESR/2019/4964) for further information requirements.

Rehabilitation area (RA) and improvement area (IA) table

- Each RA and IA table contains two parts (yellow and blue) for recording the time-based rehabilitation milestones.

- A default value of one (1) RA is represented by one RA table below (RA1).

  - To record additional RAs for your project, make a copy of the RA table below and update it to the relevant RA number (.e.g., RA2).

- A default value of one (1) IA is represented by one IA table below (IA1).

  - To record additional IAs for your project make a copy of the IA table below and update it to the relevant IA number (e.g., IA2).

  - Delete the IA table below if there is no IA for your project.

- Add a new column or row to each table as required for your information requirements.

RA milestones and IA milestones

- Two (2) separate tables below exist for recording the "Rehabilitation area milestones" and "Improvement area milestones".

  - Delete the Improvement area milestones table if it does not apply to your project.

  - Delete additional rows in either table if they do not apply to your project.

  - See the PRC plan guideline for a list of reference milestones and further information for developing additional site-specific milestones where appropriate.

# Further Instructions when inputting Post-Mining Land Uses (PMLUs)

Headings under RA table

- Rehabilitation area - The rehabilitation area must align with the reference maps included in the rehabilitation planning part of the PRC plan and the spatial data submitted with the application. This area must have the same PMLU and same milestones applied to the whole area.

- Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the rehabilitation area prior to land becoming available for rehabilitation.

- Total size of rehabilitation area (ha) - Total size of rehabilitation area in hectares.

- First milestone reference to commence - The milestone number for the first milestone to commence must be specified. This will often be RM1 but may be a later milestone if RM1 (or later milestones) does not apply to the RA.

- Commencement of first milestone - The applicant must nominate a date for when the first milestone for the rehabilitation area will commence.

- PMLU - The PMLU must align with those identified in the rehabilitation planning part of the PRC plan including the proposed final site design and the spatial data submitted with the application.

- Date area is available - The PRCP schedule must identify when land within the rehabilitation area becomes available for rehabilitation. If the whole rehabilitation area becomes available at once there should be only one date. If the rehabilitation areas become available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.

- Cumulative area available (ha) - The PRCP schedule must identify the area of land within the rehabilitation area that will become available at a given time.

- Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed. All completion dates must be 10 December of the relevant year, as required in section 4.1 step 7 of the PRCP Guideline.

- Cumulative area achieved (ha) - The PRCP schedule must show how progressive rehabilitation is being achieved over the life of the mine. This section must reflect the proposed rehabilitation work required for the rehabilitation area to achieve stable condition. The milestone reference to be included refers back to the Rehabilitation Area Milestones table with the detailed milestone criteria. The milestones must be achieved consecutively.

Headings under Rehabilitation Area Milestones table

- Rehabilitation milestone & Milestone criteria - The “rehabilitation milestone” is a short description of the rehabilitation activities. The "milestone criteria" must be written in a manner that delivers on SMART principles and demonstrate achievement of the milestone.

# Further Instructions when inputting Non-Use Management Areas (NUMAs)

Headings under Improvement Area (IA) tables

- Improvement area - The improvement area must align with the reference maps included in the rehabilitation planning part of the PRC plan and the spatial data submitted with the application. This area must have the same NUMA and same milestones applied to the whole area.

- Relevant activities - The relevant activities must align with the activities identified in the rehabilitation planning part of the PRC plan. The relevant activities are those undertaken within the improvement area prior to land becoming available for improvement.

- Total size (ha) - Total size of improvement area in hectares.

- First milestone reference to commence - The milestone number for the first milestone to commence must be specified. This will often be MM1 but may be a later milestone if MM1 (or later milestones) does not apply to the IA, or if earlier milestones were achieved prior to the commencement of the PRCP schedule.

- Commencement of first milestone - The applicant must nominate a date for when the first milestone for the improvement area will commence.

- NUMA - The NUMA must align with those identified in the rehabilitation planning part of the PRC plan including the proposed final site design and the spatial data submitted with the application.

- Date area is available - The PRCP schedule must identify when land within the improvement area becomes available for improvement. If the whole improvement area becomes available at once there should be only one date. If the improvement areas become available progressively there should be multiple dates. These dates should reflect the information provided in the rehabilitation planning part of the PRC plan.

- Cumulative area available (ha) - The PRCP schedule must identify the area of land within the improvement area that will become available at a given time.

- Milestone completed by - The PRCP schedule must identify completion dates for milestones to be completed.

- Cumulative area achieved (ha) - The PRCP schedule must show how progressive improvement is being achieved over the life of the mine. This section must reflect the proposed management work required for the improvement area to achieve sufficient improvement. The milestone reference refers back to the Improvement Area Milestones table with the detailed milestone criteria. The milestones must be achieved consecutively.

Headings under Improvement Area Milestones table

- Management milestone & Milestone criteria - The “management milestone” is a short description of the management activities. The "milestone criteria" must be able to demonstrate achievement of the milestone.

# PART 1: Post mining land uses

## (RA1) Rehabilitation area 1

| Post-mining land uses (PMLU) |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rehabilitation area |  |  |  |  | RA1 |  |  |  |  |  |  |  |
| Relevant activities |  |  |  |  | Exploration activities, early works and ancillary infrastructure |  |  |  |  |  |  |  |
| Total rehabilitation area size (ha) |  |  |  |  | 234 |  |  |  |  |  |  |  |
| Commencement of first milestone: RM1 |  |  |  |  | 10/12/2021 |  |  |  |  |  |  |  |
| PMLU |  |  |  |  | Cattle grazing |  |  |  |  |  |  |  |
| Date area is available | 10/12/21 | 10/12/33 |  |  |  |  |  |  |  |  |  |
| Cumulative area available (ha) | 19 | 234 |  |  |  |  |  |  |  |  |  |
| Milestone completed by | 10/12/26 | 10/12/36 | 10/12/38 | 10/12/41 |  | 10/12/48 | 10/12/53 |  |  |  |  |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |  |  |  |  |
| RM1 | 19 | 19 | 234 | 234 |  |  |  |  |  |  |  |
| RM2 | 19 | 19 | 234 | 234 |  |  |  |  |  |  |  |
| RM3 | 19 | 19 | 234 | 234 |  |  |  |  |  |  |  |
| RM4 | 19 | 19 | 234 | 234 |  |  |  |  |  |  |  |
| RM5 | 19 | 19 | 234 | 234 |  |  |  |  |  |  |  |
| RM6 |  | 19 | 19 | 19 |  | 234 |  |  |  |  |  |
| RM7 |  |  |  | 19 |  | 19 | 234 |  |  |  |  |

## Rehabilitation area milestones

| Milestone reference | Rehabilitation milestone | Milestone criteria |
| --- | --- | --- |
| RM1 | Infrastructure decommissioning and removal | - All services disconnected. - All built and service infrastructure demolished and removed (except where agreed in writing by the post-mining land owner/holder). - All concrete, bitumen and aggregate removed. - All waste and rubbish removed. - All gas risers / boreholes / bleeder shaft / SIS wells decommissioned. |
| RM2 | Remediation of contaminated land | - All contamination is remediated or removed from site in accordance with relevant legislation. b) A contaminated land survey is carried out by a suitably qualified person confirming the land does not present an unacceptable risk to proposed future land uses or the environment. |
| RM3 | Landform development and reshaping | - Landform is reshaped to be free-draining with slopes ≤5% and consistent with the surrounding topography. |
| RM4 | Surface preparation | - Topsoil is placed an average thickness of 200 mm. - An assessment of soil and growth media characteristics is completed by an appropriately qualified person, and amelioration and other treatments required identified. c) Ameliorant and physical treatments are applied as identified in RM4(b), if required for RA1. |
| RM5 | Revegetation (cattle grazing) | - Completed seeding in accordance with the recommended pasture mix (grasses, cover crop and legumes) of Table RM5a – Recommended Pasture Mix, and seeding rates (up to 25kg/ha). - Conservation significant flora species and LIKT species (provided in Table RM5b – Suggested Conservation Significant Flora Species and LIKT Species) added to the pasture mix with consideration of the surrounding regional ecosystems, land use, the environment, and local seed availability. Table RM5a – Recommended Pasture Mix Common name; Scientific name; Sowing rate (kg/ha). Queensland Bluegrass; Dichanthium sericeum; 6. Buffel grass; Cenchrus ciliaris; 4. Stylo; Stylosanthes scabra; 2. Black spear grass; Heteropogon contortus; 5. Mitchell grasses; Bull Mitchell grass (Astrebla squarrosa), Curly Mitchell grass (Astrebla lappacea) and Hoop Mitchell Grass (Astrebla elymoides); 3. Shirohie millet; Echinochloa esculenta; 5. TOTAL; 25. Table RM5b – Suggested Conservation Significant Flora Species and LIKT Species Common name; Scientific name. King Bluegrass; Dichanthium queenslandicum. Finger Panic; Digitaria porrecta. Brown’s Box; Eucalyptus brownii. River Red Gum; Eucalyptus camaldulensis. Narrow-leaved Ironbark; Eucalyptus crebra. Mountain Coolibah; Eucalyptus orgadophila. Forest Red Gum; Eucalyptus tereticornis. |
| RM6 |  | - Pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per Stocktake: Balancing Supply and Demand (https://futurebeef.com.au/workshops/sustainable-grazing/stocktake-balancing-supply-demand/) (FutureBeef, 2025), as provided in Table 9-6 including: - Preferred pasture species (3P grasses1) diversity ≥2 species; - Preferred pasture (3P grasses1) % DM yield ≥10%; - Annual grass DM yield % <70%; - Undesirable grasses and other weeds % DM yield <80%; and - Crown cover (3P grasses1) – at worst, moderate to low density and some plants dead. 13P grasses: native and naturalised exotic grass species that are perennial, palatable, and productive plants to stock. |
| RM7 |  | - A hazard assessment has been completed by an appropriately qualified person to confirm safety hazards in rehabilitation are not significantly different to surrounding unmined landscapes subject to the same land use. - Groundcover2 >50%. - Rainfall runoff from the area is not significantly different to upstream values for the following: pH, EC and turbidity. - Land suitability class ≤3, or not different from pre-mining class if ≥4, as per Table RM7 – Land Suitability Rule-Set (Cattle Grazing). The assessment is to be conducted by an appropriately qualified person and completed in accordance with LSA Framework for Open-Cut Coal Mine Rehabilitation 2018 (A rule-set for land suitability assessment of sustainable beef cattle grazing on land rehabilitated after open-cut coal mining in the Bowen Basin Queensland) unless otherwise agreed in writing between the administering authority and the environmental authority holder. For RM7(f), if the land suitability class is assessed as not different from pre-mining class if ≥4 for all or a portion of a rehabilitation area, an assessment of reference sites3 must be carried out to determine if the limitation/s resulting in the class of ≥4 is consistent with that of reference sites. - Certification by an appropriately qualified person that pasture meets a pasture condition rating ≤3, based on the Pasture Condition Assessment Table as per Stocktake: Balancing Supply and Demand, as provided in Table 9-6. - All subsidence impacts are remediated. 2Groundcover: to anything in contact with the soil surface, for example, rocks, stones, sticks, leaves, grass, hay 3Reference site: representative undisturbed grazing land adjacent to the disturbance areas Table RM7 – Land Suitability Rule-Set (Cattle Grazing) Limitation; Indicator; Units; Suitability class. 1; 2; 3; 4; 5. Water availability; PAWC in ERD; mm/0.6d; > 75; 75 - 60; < 60 - 45; < 45 - 30; < 30. Nutrient supply; P in 0.1m; mg / kg; > 20; 20 - 14; < 14 - 8; < 8 - 4; < 4. pH in 0.1m; pH units units; 7.3 – 6.6; < 6.6. – 6.0 or > 7.3 – 8.0; < 6.0 – 5.5 or > 8.0 – 8.5; < 5.5 – 5.0 or > 8.5 – 9.0; < 5.0 or > 9.0. Soil physical factors; Surface soil structure; variable; Fine (peds < 10mm); Coarse (peds > 10mm); Surface crust; Very hard setting; Massive. Salinity; EC in ERD; dS/m; < 2; 2 - < 4; 4 - < 10; 10 - < 16; ≥ 16. Rockiness; Fragments on surface; %; < 5; 5 - 10; 10 - 30; 30 - 60; > 60. Topography (slope); Gradient, surface; %; < 5; 5 - < 10; 10 - < 15; 15 - < 20; ≥ 20. Vertical interval, surface; m; Nil ripping furrows; Regular ripping furrows < 0.2m; Regular ripping furrows > 0.2 – 0.4m; Regular ripping furrows > 0.4 – 0.6m; Regular ripping furrows > 0.6m. Water erosion, surface soil; Slope (ESP in 0.1m <6); %; < 5; 5 - 8; > 8 - 12; > 12 - 18; > 18. Slope (ESP in 0.1m > 6 - < 14); %; < 3; 3 - 6; > 6 - 10; > 10 - 12; > 12. Slope (ESP in 0.1m > 14); %; < 1; 1 - 2; > 2 - 4; > 4 - 6; > 6. Sub-soil erosion; ESP at 0.5m; %; < 7; 7 - 14; > 14 - 23; > 23 - 34; > 34. PAF materials; pH < 4.5; pH units; Not likely to be present within 5m of surface; Not likely to be present within 3m of surface; Not likely to be present within 2m of surface; Present immediately below root zone (0.9 – 0.6m); Present within root zone (surface 0.6m). |

# PART 2: Non-use management areas – Not applicable

## (IA1) Improvement area 1

| Non-use management area (NUMA) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improvement area |  |  |  |  | Not applicable |  |  |  |  |  |  |
| Relevant activities |  |  |  |  |  |  |  |  |  |  |  |
| Total size (ha) |  |  |  |  |  |  |  |  |  |  |  |
| Commencement of first milestone: RM1 |  |  |  |  |  |  |  |  |  |  |  |
| NUMA |  |  |  |  |  |  |  |  |  |  |  |
| Date area is available |  |  |  |  |  |  |  |  |  |  |  |
| Cumulative area available (ha) |  |  |  |  |  |  |  |  |  |  |  |
| Milestone completed by |  |  |  |  |  |  |  |  |  |  |  |
| Milestone Reference | Cumulative area achieved (ha) |  |  |  |  |  |  |  |  |  |  |
| RM## |  |  |  |  |  |  |  |  |  |  |  |
| RM## |  |  |  |  |  |  |  |  |  |  |  |
| RM## |  |  |  |  |  |  |  |  |  |  |  |
| RM## |  |  |  |  |  |  |  |  |  |  |  |
| RM## |  |  |  |  |  |  |  |  |  |  |  |

## Improvement area milestones – Not applicable

| Milestone reference | Management milestone | Milestone criteria |
| --- | --- | --- |
| MM1 |  |  |
| MM2 |  |  |
| MM3 |  |  |
| MM4 |  |  |
| MM5 |  |  |
| MM6 |  |  |
| MM7 |  |  |
| MM8 |  |  |
| MM9 |  |  |
| MM10 |  |  |

# PART 3: Maps

The following two maps must be included in the application and will form part of the approved PRCP Schedule (see PRCP Guideline (ESR/2019/4964) for examples). Attach the maps to the application as high-resolution jpeg files.

# Final site design

A final site design has the purpose of showing the community what the site will look like post surrender, and must depict:

- All Post Mining Land Uses (PMLU) and Non-Use Management Areas (NUMA) for all land within the relevant resource tenures, including undisturbed land

- Maximum disturbance footprint

- Resource tenure boundaries

- Floodplain extent (if relevant).

# Reference map(s)

Reference map(s) have the purpose of showing the boundary of each rehabilitation area (for PMLUs) and improvement area (for NUMAs). Reference maps may contain more than one rehabilitation area/improvement area and must be to a scale that allows for easy interpretation. Only areas of disturbance need to be included on these reference maps.